## Sheet1
Name | Start Date | End Date | Duration (days)
Requirements Analysis | 2024-11-14 | 2024-11-18 | 5
Database Design (ERD & Planning) | 2024-11-19 | 2024-11-23 | 5
Web Application Design (UI/UX & Sitemap) | 2024-11-24 | 2024-11-28 | 5
Development - Database & Backend | 2024-11-29 | 2024-12-06 | 8
Development - Frontend & Integration | 2024-12-07 | 2024-12-12 | 6
Testing (Functionality, UX, and Responsiveness) | 2024-12-13 | 2024-12-17 | 5
Deployment & Final Adjustments | 2024-12-18 | 2024-12-20 | 3